## BC T5
| CÔNG TY TNHH THU LỘC |  | CỘNG HOÀ XÃ HỘI CHỦ NGHĨA VIỆT NAM
Độc Lập - Tự Do - Hạnh Phúc
Xuân Lộc, ngày 03 tháng 10 năm 2019
BÁO CÁO TIẾN ĐỘ THỰC HIỆN THI CÔNG XÂY DỰNG CÔNG TRÌNH
Công trình: Nâng cấp đường dây trung thế từ recloser Xuân Bắc đến LBS Khí Chế Biến Tuyến 480 Xuân Bắc
| Đơn vị Thi công | Công ty TNHH Thu Lộc |  |  |  |  | Ngày khởi công: 23/8/2019 | [5 empty] | 2019-08-23
| Ngày hoàn thành: 30/11/2019 |  | Thời gian thi công đến ngày báo cáo: |  |  |  |  | 48 | ngày |  |  |  | 2019-10-10
STT | Nội dung công việc chính | Đơn vị | Khối lượng theo hợp đồng | Khối lượng theo thực tế | Khối lượng đăng ký thực hiện trong tuần |  | Khối lượng thực hiện trong tuần |  | Luỹ kế từ khi khởi công đến ngày báo cáo |  | Chi chú | 2019-10-03 | 2019-10-10
[5 empty] | KL | Tlệ % | KL | Tlệ % | KL | Tlệ %
I | Khôi lượng thực hiện trong tuần
1 | Phòng tuyến phân bố trụ | Vị trí | 101 | 101 |  | 0% |  | 0% | 101 | 100% |  | 101
2 | Móng M12 | Móng | 36 | 36 |  | 0% |  | 0% | 36 | 100% |  | 36
3 | Đào lổ trụ M12a | Móng | 40 | 40 |  | 0% |  | 0% | 72 | 180% |  | 0 | 72
4 | Đào lổ trụ M12-BT đôi | Móng | 10 | 10 |  | 0% |  | 0% | 10 | 100% |  | 10
5 | Móng M14a | Móng | 15 | 15 |  | 0% |  | 0% | 2 | 13.33% |  | 2 | 11
6 | Đào lổ neo | Móng | 2 | 2 |  | 0% |  | 0% | 2 | 100% |  | 2
7 | Trồng trụ BTLT12m | Trụ | 96 | 96 |  | 0% |  | 0%
8 | Trồng trụ BTLT14m | Trụ | 15 | 15 |  | 0% |  | 0%
9 | Lắp đặt móng đà cản M12a | Móng | 40 | 40 |  | 0% |  | 0%
10 | Lắp neo các loại | Bộ | 2 | 2 |  | 0% |  | 0%
11 | Lắp tiếp địa lặp lại | Bộ | 39 | 39 |  | 0% |  | 0%
12 | Lắp xà | Bộ
13 | Lắp sứ đứng | Bộ
14 | Lắp sứ chuỗi | Bộ
15 | Thay dây | mét | 6.338 | 6.338
16 | Tháo lắp trạm biến áp 1P - 75KVA | Trạm | 2 | 2
17 | Tháo lắp trạm biến áp 1P - 100KVA | Trạm | 9 | 9
I | Khối lượng thực hiện tuần tới :
1 | Móng M14a | Móng | 15 | 15 | 7 | 46.67%
2 | Đào lổ neo | Móng | 2 | 2
3 | Trồng trụ BTLT12m | Trụ | 96 | 96 | 62 | 64.58%
4 | Trồng trụ BTLT14m | Trụ | 15 | 15 | 6 | 40%
5 | Lắp đặt móng đà cản M12a | Móng | 40 | 40
6 | Lắp neo các loại | Bộ | 2 | 2
7 | Lắp tiếp địa lặp lại | Bộ | 39 | 39
8 | Lắp xà | Bộ | 174 | 174 | 100 | 57.47%
9 | Lắp sứ đứng | Bộ | 591 | 591 | 360 | 60.91%
10 | Lắp sứ chuỗi | Bộ | 93 | 93 | 51 | 54.84%
11 | Thay dây | mét | 6.338 | 6.338
12 | Tháo lắp trạm biến áp 1P - 75KVA | Trạm | 2 | 2
13 | Tháo lắp trạm biến áp 1P - 100KVA | Trạm | 9 | 9 | 6 | 66.67%
Ghi chú: - Cắt điện thi công ngày thứ 1 (05/10/2019) thi công trồng trụ, thay trụ trạm, lắp đặt xà, sứ (từ trụ 090 - 142)
| Đội trưởng thi công |  |  | Giám sát B |  |  |  | Giám sát A
| Nguyễn Tân Long |  |  | Hoàng Như Hoàn

## Sheet1
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!